## Slide 1
Financial
Monitoring
& Burn Rate
UNJP/URT/167/UNJ
Data for Digital Agriculture Transformation (D4DAT)
TF5C35TZ24481 · FAO Trust Fund
FI 102
September 2026
TOTAL BUDGET
$950,017
BURN RATE
27.6%
AVAILABLE
$550,793
Run: 22-Sep-2026 · Period: Nov 1997 – Dec 2030

## Slide 2
Key Performance Indicators
FI 102 | September 2026
Source: FI 102 – TF Financial Statement | TF5C35TZ24481 | 22-Sep-2026
D4DAT Joint Programme | September 2026
TOTAL BUDGET
$950,017
Approved allocation
FUNDS RECEIVED
$593,696
Contributions received
TOTAL ACTUALS
$262,104
Expenditure to date
TOTAL COMMITMENTS
$137,120
Soft $90,121 · Hard $46,999
BURN RATE
27.6%
Actuals / Total Budget
Budget Utilization
$262,104 actuals spent of $950,017 total budget. Overall burn rate 27.6% — project in early-to-mid execution phase.
Commitment Status
Total commitments $137,120 (Soft $90,121 + Hard $46,999). Combined exposure $399,224 = 42% of approved budget.
Funding Position
Funds received $593,696 = 62.5% of approved budget. Outstanding balance $356,321. Available budget: $550,793.

## Slide 3
Budget Allocation vs Actuals by Category (USD)
All figures in USD
Source: FI 102 – TF Financial Statement | TF5C35TZ24481 | 22-Sep-2026
D4DAT Joint Programme | September 2026
Chart: 
| Consultants | Contracts | Travel | Training | Exp. Proc. | Non-Exp. Eq. | Tech. Support | Gen. Operating | Support Costs | Workshop | Common Svcs
Budget | 89636 | 452248 | 134866 | 2215 | 78832 | 12352 | 44128 | 50539 | 62151 | 0 | 23050
Actuals | 82180 | 0 | 95127 | 14420 | 6890 | 0 | 11057 | 11662 | 17008 | 5731 | 18029
Commitments | 5612 | 90000 | 2165 | 0 | 4576 | 34646 | 0 | 121 | 0 | 0 | 0

## Slide 4
Burn Rate & Delivery Analysis
As of 22-Sep-2026
Source: FI 102 – TF Financial Statement | TF5C35TZ24481 | 22-Sep-2026
D4DAT Joint Programme | September 2026
Chart: 
| Burned (27.6%) | Available (72.4%)
 | 27.6 | 72.4
27.6%
BURNED
$262,104 / $950,017
Actuals / Total Budget
$399,224
Commitments & Actuals
$550,793
Available Budget
$593,696
Funds Received
⚠ 3 line items have budget overruns — see Slide 6 for details

## Slide 5
Budget Summary by Line Item
TF5C35TZ24481
Source: FI 102 – TF Financial Statement | TF5C35TZ24481 | 22-Sep-2026
D4DAT Joint Programme | September 2026
Line Item
Budget ($)
Actuals ($)
Commits ($)
Burn %
Available ($)
Consultants
89,636
82,180
5,612
91.7%
1,844
Contracts
452,248
0
90,000
0%
362,248
Travel
134,866
95,127
2,165
70.5%
37,574
Training
2,215
14,420
0
651%
(12,205)
Expendable Proc.
78,832
6,890
4,576
8.7%
67,366
Non-Exp. Equip.
12,352
0
34,646
0%
(22,294)
Tech. Support Svcs
44,128
11,057
0
25.1%
33,071
General Operating
50,539
11,662
121
23.1%
38,756
Support Costs
62,151
17,008
0
27.4%
45,143
Workshop Expenses
0
5,731
0
N/A
(5,731)
Common Svcs (DSC)
23,050
18,029
0
78.2%
5,021
TOTAL
950,017
262,104
137,120
27.6%
550,793
* Non-Exp. Equip. (5025): Hard commitments of $34,646 exceed budget of $12,352 by $22,294.

## Slide 6
Budget Overrun Alerts
3 Items Require Immediate Attention
Source: FI 102 – TF Financial Statement | TF5C35TZ24481 | 22-Sep-2026
D4DAT Joint Programme | September 2026
5023
Training
651%
Budget:
$2,215
Actuals:
$14,420
Over by:
$12,205
Actual expenditure exceeded original budget by 551%. Immediate budget review and reallocation required.
5025
Non-Expendable Equipment
Commit Risk
Budget:
$12,352
Actuals:
$0 spent
Over by:
$22,294
Hard commitments of $34,646 exceed the $12,352 budget. No actuals yet but commitment exposure is over-budget.
5031
Workshop Expenses
Unbudgeted
Budget:
$0
Actuals:
$5,731
Over by:
$5,731
Expenditure incurred against a $0 budget line. Budget reallocation or supplemental funding required.